## q1-action-plan
Get Accelerated Planning System (GAPS)
Example: Growing Sales
© 2022 MKG, LLC DBA PeopleInsure. All Rights Reserved. Confidential, for use by registers participants only.
Plan Action | Subitems | Person | Status | Start Date | Due Date | Timeline - Start | Timeline - End | Summary Notes | Item ID (auto generated)
Subitems | Name | Owner | Status | Date | Due Date | Timeline - Start | Timeline - End | Resource | Summary | Item ID (auto generated)
Q1 Action Plan
The Plan
Goal |  | RL Koos | Completed | 2022-12-01 | 2022-12-11 | 2022-12-01 | 2022-12-11 |  | 3615071872
Strategy |  | RL Koos | Completed | 2022-12-02 | 2022-12-11 | 2022-12-01 | 2022-12-11 |  | 3615071871
Performance Level |  | RL Koos | Waiting for ... | 2022-12-01 | 2022-12-11 | 2022-12-01 | 2022-12-11 |  | 3615100411
High Level Plan |  | RL Koos | Completed | 2022-12-01 | 2022-12-11 | 2022-12-01 | 2022-12-11 |  | 3615071873
KPIs |  | RL Koos | Completed | 2022-12-01 | 2022-12-11 | 2022-12-01 | 2022-12-11 |  | 3615100172
|  |  |  | 2022-12-01 to 2022-12-02 | 2022-12-11 | 2022-12-01 | 2022-12-11
Plan & Prep
Create Plan |  | RL Koos | Waiting for ... | 2022-12-01 | 2022-12-12 | 2022-12-03 | 2022-12-12 |  | 3615133035
| Complete GAPS Planning Sessions | RL Koos | Not Started Yet | 2022-12-01 | 2022-12-08 |  |  |  |  | 3615133181
| Complete workbook | RL Koos | Not Started Yet |  | 2022-12-09 |  |  |  |  | 3615138153
| Setup Project Tracking Method | RL Koos | Not Started Yet |  | 2022-12-12 |  |  |  |  | 3615138253
Gather Resources |  | RL Koos | Waiting for ... |  | 2022-12-15 | 2022-12-12 | 2022-12-15 |  | 3615139210
| Setup AMS for tracking KPIs | rkoos@peopleinsure.com | Not Started Yet | [6 empty] | 3615142190
| Setup CRM for tracking KPIs | rkoos@peopleinsure.com | Not Started Yet | [6 empty] | 3615142383
| Get New Campaign Software | rkoos@peopleinsure.com | Not Started Yet | [6 empty] | 3615142723
| Setup New Campaign Software | rkoos@peopleinsure.com | Not Started Yet | [6 empty] | 3615142862
Build & Enroll Team |  | RL Koos | Not Started Yet |  | 2022-12-15 | 2022-12-15 | 2022-12-16 |  | 3615139446
| Meet with Acct Team to get feedback, ideas, align goals, buying action plans | RL Koos | Not Started Yet | [6 empty] | 3615152459
| ID team member goals, KPIs & needs | RL Koos | Not Started Yet | [6 empty] | 3615152586
| Negotiate agreement | RL Koos | Not Started Yet | [6 empty] | 3615152664
| Hire SEO Expert | RL Koos | Not Started Yet | [6 empty] | 3615149408
| Find Copywriter Consultant | RL Koos | Not Started Yet | [6 empty] | 3615152130
Establish Baseline KPIs |  | RL Koos | Not Started Yet |  | 2022-12-19 | 2022-12-16 | 2022-12-19 |  | 3615139831
| Run EOY reports for KPIs | rkoos@peopleinsure.com | Not Started Yet | [6 empty] | 3615153131
| Cleanup data consistency issues for comparisons | rkoos@peopleinsure.com | Not Started Yet | [6 empty] | 3615153283
Setup Enabling Technology |  | RL Koos | Not Started Yet |  | 2022-12-21 | 2022-12-19 | 2022-12-21 |  | 3615141317
| Setup new CRM | rkoos@peopleinsure.com | Not Started Yet | [6 empty] | 3615165557
| Update LinkedIn Account / Profile | RL Koos | Not Started Yet | [6 empty] | 3615165687
| SEO Optimization (Consultant) | rkoos@peopleinsure.com | Not Started Yet | [6 empty] | 3615165861
| Clean email list | rkoos@peopleinsure.com | Not Started Yet | [6 empty] | 3615182246
Design Rounding Campaign |  | RL Koos | Not Started Yet |  | 2022-12-23 | 2022-12-21 | 2022-12-23 |  | 3615153407
| Identify Persona | RL Koos | Not Started Yet | [6 empty] | 3615162866
| Identify Offering | RL Koos | Not Started Yet | [6 empty] | 3615163009
| Determine messaging | RL Koos | Not Started Yet | [6 empty] | 3615153770
| Outline high level campaign steps | RL Koos | Not Started Yet | [6 empty] | 3615153636
| Determine automated vs personal touches | RL Koos | Not Started Yet | [6 empty] | 3615163311
| Determine Ad Budget | RL Koos | Not Started Yet | [6 empty] | 3615164007
| Identify ad placement | RL Koos | Not Started Yet | [6 empty] | 3615164450
| Enter into CRM | RL Koos | Not Started Yet | [6 empty] | 3615153709
Design Referral Campaign |  | RL Koos | Not Started Yet |  | 2022-12-23 | 2022-12-21 | 2022-12-23 |  | 3615890454
| Identify Persona | RL Koos | Not Started Yet | [6 empty] | 3615890470
| Identify Offering | RL Koos | Not Started Yet | [6 empty] | 3615890473
| Determine messaging | RL Koos | Not Started Yet | [6 empty] | 3615890466
| Outline high level campaign steps | RL Koos | Not Started Yet | [6 empty] | 3615890459
| Determine automated vs personal touches | RL Koos | Not Started Yet | [6 empty] | 3615890476
| Determine Ad Budget | RL Koos | Not Started Yet | [6 empty] | 3615890480
| Identify ad placement | RL Koos | Not Started Yet | [6 empty] | 3615890484
| Enter into CRM | RL Koos | Not Started Yet | [6 empty] | 3615890463
Design New Business Plans (copy) |  | RL Koos | Not Started Yet |  | 2022-12-23 | 2022-12-21 | 2022-12-23 |  | 3615892861
| Identify Persona | RL Koos | Not Started Yet | [6 empty] | 3615893071
| Identify Offering | RL Koos | Not Started Yet | [6 empty] | 3615893103
| Determine messaging | RL Koos | Not Started Yet | [6 empty] | 3615893037
| Outline high level campaign steps | RL Koos | Not Started Yet | [6 empty] | 3615892949
| Determine automated vs personal touches | RL Koos | Not Started Yet | [6 empty] | 3615893141
| Determine Ad Budget | RL Koos | Not Started Yet | [6 empty] | 3615893167
| Identify ad placement | RL Koos | Not Started Yet | [6 empty] | 3615893196
| Enter into CRM | RL Koos | Not Started Yet | [6 empty] | 3615892998
Develop Assets |  | RL Koos | Not Started Yet |  | 2022-12-31 | 2022-12-27 | 2022-12-31 |  | 3615140167
| Create initial ads | rkoos@peopleinsure.com | Not Started Yet | [6 empty] | 3615154058
| Write emails | rkoos@peopleinsure.com | Not Started Yet | [6 empty] | 3615154165
| Write video script | rkoos@peopleinsure.com | Not Started Yet | [6 empty] | 3615154267
| Shoot video | RL Koos | Not Started Yet | [6 empty] | 3615154419
| Post Video | rkoos@peopleinsure.com | Not Started Yet | [6 empty] | 3615154521
| Write lead magnet report | rkoos@peopleinsure.com | Not Started Yet | [6 empty] | 3615165175
| Create landing page | rkoos@peopleinsure.com | Not Started Yet | [6 empty] | 3615165374
Build Performance Skills |  | RL Koos | Not Started Yet |  | 2022-12-31 | 2022-12-03 | 2022-12-31 |  | 3615166056
| Read book on Sales | RL Koos | Not Started Yet | [6 empty] | 3615166249
| Read omni-channel sales articles | RL Koos | Not Started Yet | [6 empty] | 3615166370
| Take sales class to sharpen skills, additional ideas | RL Koos | Not Started Yet | [6 empty] | 3615166720
| Hire a coach |  | Not Started Yet | [6 empty] | 3615166778
ID Insurance Market |  |  | Not Started Yet | [5 empty] | 3616060493
Performance Improvement Plan
Reading - 1 Sales Book/Mo |  | RL Koos | Working on it |  | 2022-12-23 | 2022-12-21 | 2022-12-23 |  | 3615911006
| Jan - To Sell is Human | RL Koos | Not Started Yet | [6 empty] | 3615911219
| Feb - Influence: The Psychology of Persuasion b | RL Koos | Not Started Yet | [6 empty] | 3615911222
| Mar - Strategic Selling | RL Koos | Not Started Yet | [6 empty] | 3615911215
| Apr - Sales Scripting Mastery | RL Koos | Not Started Yet | [6 empty] | 3615911212
| May - Endless Referrals | RL Koos | Not Started Yet | [6 empty] | 3615911225
| June - Pitch Anything | RL Koos | Not Started Yet | [6 empty] | 3615911231
| July - Secrets of Closing the Sale | RL Koos | Not Started Yet | [6 empty] | 3615911233
| Aug - The Psychology of Selling by Brian Tracy | RL Koos | Not Started Yet | [6 empty] | 3615911214
| Sept - SNAP Selling |  | Not Started Yet | [6 empty] | 3615912258
| Oct - New Sales Simplified |  | Not Started Yet | [6 empty] | 3615912314
| Nov - Spin Selling |  | Not Started Yet | [6 empty] | 3615912344
| Dec - Never Split the Difference |  | Not Started Yet | [6 empty] | 3615912388
Read - 1 Marketing Article / week |  | RL Koos | Working on it | 2022-12-05 |  |  |  |  | 3615933496
| W1 | RL Koos | Completed |  | 2023-01-07 |  |  |  |  | 3615933504
| W2 | RL Koos | Not Started Yet |  | 2023-01-14 |  |  |  |  | 3615933508
| W3 | RL Koos | Not Started Yet |  | 2023-01-21 |  |  |  |  | 3615933513
| W4 | RL Koos | Not Started Yet |  | 2023-01-28 |  |  |  |  | 3615933518
| W5 | RL Koos | Not Started Yet |  | 2023-02-04 |  |  |  |  | 3615933522
| W6 | RL Koos | Not Started Yet |  | 2023-02-11 |  |  |  |  | 3615933528
| W7 | RL Koos | Not Started Yet |  | 2023-02-18 |  |  |  |  | 3615933530
| W8 | RL Koos | Not Started Yet |  | 2023-02-25 |  |  |  |  | 3615933534
| W9 | RL Koos | Not Started Yet |  | 2023-03-04 |  |  |  |  | 3615933536
| W10 | RL Koos | Not Started Yet |  | 2023-03-11 |  |  |  |  | 3615933543
| W11 | RL Koos | Not Started Yet |  | 2023-03-18 |  |  |  |  | 3615933546
| W12 | RL Koos | Not Started Yet |  | 2023-03-25 |  |  |  |  | 3615933557
| W13 | RL Koos | Not Started Yet |  | 2023-03-31 |  |  |  |  | 3615933561
Sales Training |  | RL Koos | Working on it |  | 2022-12-23 | 2022-12-21 | 2022-12-23 |  | 3615911013
| Register for training | RL Koos | Not Started Yet | [6 empty] | 3615911277
| Do Program | RL Koos | Not Started Yet | [6 empty] | 3615911280
| Review Program | RL Koos | Not Started Yet | [6 empty] | 3615911275
| Determine Ad Budget | RL Koos | Not Started Yet | [6 empty] | 3615911284
Sales Coaching |  | RL Koos | Working on it |  | 2022-12-23 | 2022-12-21 | 2022-12-23 |  | 3615911010
| Get a coach | RL Koos | Not Started Yet |  | 2023-01-01 |  |  |  |  | 3615911247
| S1 Actions | RL Koos | Not Started Yet |  | 2023-01-07 |  |  |  |  | 3615911251
| S2 Actions | RL Koos | Not Started Yet |  | 2023-01-14 |  |  |  |  | 3615911244
| S3 Actions | RL Koos | Not Started Yet |  | 2023-01-21 |  |  |  |  | 3615911242
| S4 Actions | RL Koos | Not Started Yet |  | 2023-01-28 |  |  |  |  | 3615911252
| S5 Actions | RL Koos | Not Started Yet |  | 2023-02-04 |  |  |  |  | 3615911255
| S6 Actions | RL Koos | Not Started Yet |  | 2023-02-11 |  |  |  |  | 3615911259
| S7 Actions | RL Koos | Not Started Yet |  | 2023-02-18 |  |  |  |  | 3615911243
CLV: SIMPLE Account Round (Clients)
Plan & Prep |  | rkoos@peopleinsure.com | Working on it | 2022-12-27 | 2022-12-30 | 2022-12-30 | 2022-12-30 |  | 3615123506
| Client LOB Report | RL Koos | Not Started Yet | 2022-12-30 |  |  |  | PR Touch | Run & Review for Account Rounding Opportunities | 3633386790
| Determine approach | RL Koos | Not Started Yet | 2022-12-30 |  |  |  | PR Touch | Determine initial Approach to Clients; what if yes, no, maybe, no answer | 3615123509
| Setup KPI Measurement Tracking |  | Not Started Yet | 2022-12-30 |  |  |  | CRM Entry | Track Results | 3633380671
| Notify Staff |  | Not Started Yet | 2022-12-30 |  |  |  | PR Touch | Let staff know what doing | 3633379088
Client Calls |  | RL Koos | Not Started Yet | 2022-12-05 | 2022-12-30 | 2023-01-03 | 2023-03-31 | 10/wk | 3615198061
| W1 | RL Koos | Not Started Yet |  | 2023-01-07 |  |  | PR Touch |  | 3615198066
| W2 | RL Koos | Not Started Yet |  | 2023-01-14 |  |  | PR Touch |  | 3615198067
| W3 | RL Koos | Not Started Yet |  | 2023-01-21 |  |  | PR Touch |  | 3615198070
| W4 | RL Koos | Not Started Yet |  | 2023-01-28 |  |  | PR Touch |  | 3615198072
| W5 | RL Koos | Not Started Yet |  | 2023-02-04 |  |  | PR Touch |  | 3615198073
| W6 | RL Koos | Not Started Yet |  | 2023-02-11 |  |  | PR Touch |  | 3615198075
| W7 | RL Koos | Not Started Yet |  | 2023-02-18 |  |  | PR Touch |  | 3615198076
| W8 | RL Koos | Not Started Yet |  | 2023-02-25 |  |  | PR Touch |  | 3615198077
| W9 | RL Koos | Not Started Yet |  | 2023-03-04 |  |  | PR Touch |  | 3615198078
| W10 | RL Koos | Not Started Yet |  | 2023-03-11 |  |  | PR Touch |  | 3615198079
| W11 | RL Koos | Not Started Yet |  | 2023-03-18 |  |  | PR Touch |  | 3615198080
| W12 | RL Koos | Not Started Yet |  | 2023-03-25 |  |  | PR Touch |  | 3615198083
| W13 | RL Koos | Not Started Yet |  | 2023-03-31 |  |  | PR Touch |  | 3615198086
KPI Review |  | RL Koos | Not Started Yet | 2023-01-07 |  |  |  |  | 3615071874
| W1 | RL Koos | Not Started Yet |  | 2023-01-07 |  |  | Team - Promo+Sales |  | 3615185619
| W2 | RL Koos | Not Started Yet |  | 2023-01-14 |  |  | Team - Promo+Sales |  | 3615185641
| W3 | RL Koos | Not Started Yet |  | 2023-01-21 |  |  | Team - Promo+Sales |  | 3615185677
| W4 | RL Koos | Not Started Yet |  | 2023-01-28 |  |  | Team - Promo+Sales |  | 3615185714
| W5 | RL Koos | Not Started Yet |  | 2023-02-04 |  |  | Team - Promo+Sales |  | 3615186620
| W6 | RL Koos | Not Started Yet |  | 2023-02-11 |  |  | Team - Promo+Sales |  | 3615186888
| W7 | RL Koos | Not Started Yet |  | 2023-02-18 |  |  | Team - Promo+Sales |  | 3615186936
| W8 | RL Koos | Not Started Yet |  | 2023-02-25 |  |  | Team - Promo+Sales |  | 3615186956
| W9 | RL Koos | Not Started Yet |  | 2023-03-04 |  |  | Team - Promo+Sales |  | 3615186980
| W10 | RL Koos | Not Started Yet |  | 2023-03-11 |  |  | Team - Promo+Sales |  | 3615187000
| W11 | RL Koos | Not Started Yet |  | 2023-03-18 |  |  | Team - Promo+Sales |  | 3615187027
| W12 | RL Koos | Not Started Yet |  | 2023-03-25 |  |  | Team - Promo+Sales |  | 3615187124
| W13 | RL Koos | Not Started Yet |  | 2023-03-31 |  |  | Team - Promo+Sales |  | 3615187141
Improve / Adapt |  | RL Koos | Not Started Yet | 2023-01-07 |  |  |  |  | 3615187931
| Improvement Based on Results |  | Not Started Yet | [6 empty] | 3633337579
| Improvement Based on Results |  | Not Started Yet | [6 empty] | 3633342836
| Improvement Based on Results |  | Not Started Yet | [6 empty] | 3633343228
|  |  |  | 2022-12-05 to 2023-01-07 | 2022-12-30 | 2022-12-30 | 2023-03-31
CLV: Account Round (Clients)
Plan & Prep |  | rkoos@peopleinsure.com | Working on it | 2023-01-01 | 2023-01-15 | 2023-01-01 | 2023-01-15 |  | 3639985727
| Research | RL Koos | Not Started Yet |  |  |  |  | Team - Promo+Sales |  | 3639988086
| Map Campaign | RL Koos | Not Started Yet |  |  |  |  | Team - Promo+Sales |  | 3639987819
| Develop Content & Assets |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3639987857
| List - Reports fr AMS |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3639987960
| CRM Load Map & Content |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3639987901
| Setup KPI Measurement Tracking |  | Not Started Yet |  |  |  |  | Team - Promo+Sales | Track Results | 3639988048
| Train Staff |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3639988007
| Test & AB Test |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3639987934
Campaign Map - DRIP |  | rkoos@peopleinsure.com | Not Started Yet | 2023-01-01 | 2023-01-15 | 2023-01-01 | 2023-01-15 | Drip Campaign | 3639985602
| LinkedIn & You Tube Video Post |  | Not Started Yet |  |  |  |  | Social Media/Online |  | 3639987067
| Email |  | Not Started Yet |  |  |  |  | CRM Email Automated |  | 3639987101
| Email |  | Not Started Yet |  |  |  |  | CRM Email Automated |  | 3639987135
| Email |  | Not Started Yet |  |  |  |  | CRM Email Automated |  | 3639987164
| Call |  | Not Started Yet |  |  |  |  | PR Touch | CRM Notifies PR #~ | 3639987208
| Client To Sold Onboarding Campaign |  | Not Started Yet |  |  |  |  | CSR |  | 3639987235
| Client To Nurture Campaign |  | Not Started Yet |  |  |  |  | CRM Email Automated |  | 3639987362
Launch |  | RL Koos, rkoos@peopleinsure.com | Not Started Yet | 2023-01-16 | 2023-01-16 | 2023-01-16 | 2023-01-31 |  | 3639985419
| Beta Launch |  | Not Started Yet | 2023-01-16 | 2023-01-31 | 2023-01-16 | 2023-01-31 | Marketing Staff |  | 3639986663
| Improvements |  | Not Started Yet | 2023-02-01 | 2023-02-05 | 2023-02-01 | 2023-02-05 | Team - Promo+Sales |  | 3639986733
| General launch | rkoos@peopleinsure.com | Not Started Yet | 2023-02-06 | 2023-02-06 | 2023-02-06 | 2023-03-31 | Marketing Staff |  | 3639986312
| LinkedIn Posts | rkoos@peopleinsure.com | Not Started Yet | 2023-01-01 | 2023-03-31 | 2023-01-01 | 2023-03-31 | Tech - SM Sched Post |  | 3639986417
| See CRM for tracking touches and sales KPIs | RL Koos | Not Started Yet |  |  |  |  | CRM Entry | CRM docs touches not automated | 3639986503
Manage Campaign |  | rkoos@peopleinsure.com | Not Started Yet | 2023-01-16 | 2023-03-31 | 2023-01-01 | 2023-03-31 |  | 3639985680
| Review CRM |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3639987473
| Test |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3639987509
| Resolve Issues |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3639987556
| Answer Questions |  | Not Started Yet |  |  |  |  | Team - Promo+Sales |  | 3639987581
| Improve |  | Not Started Yet |  |  |  |  | Team - Promo+Sales |  | 3639987530
KPI Review |  | RL Koos | Not Started Yet | 2023-01-01 |  | 2023-01-01 | 2023-03-31 |  | 3639985201
| W1 | RL Koos | Not Started Yet |  | 2023-01-07 |  |  | Team - Promo+Sales |  | 3639985842
| W2 | RL Koos | Not Started Yet |  | 2023-01-14 |  |  | Team - Promo+Sales |  | 3639985880
| W3 | RL Koos | Not Started Yet |  | 2023-01-21 |  |  | Team - Promo+Sales |  | 3639985951
| W4 | RL Koos | Not Started Yet |  | 2023-01-28 |  |  | Team - Promo+Sales |  | 3639986109
| W5 | RL Koos | Not Started Yet |  | 2023-02-04 |  |  | Team - Promo+Sales |  | 3639986190
| W6 | RL Koos | Not Started Yet |  | 2023-02-11 |  |  | Team - Promo+Sales |  | 3639986251
| W7 | RL Koos | Not Started Yet |  | 2023-02-18 |  |  | Team - Promo+Sales |  | 3639986310
| W8 | RL Koos | Not Started Yet |  | 2023-02-25 |  |  | Team - Promo+Sales |  | 3639986406
| W9 | RL Koos | Not Started Yet |  | 2023-03-04 |  |  | Team - Promo+Sales |  | 3639986475
| W10 | RL Koos | Not Started Yet |  | 2023-03-11 |  |  | Team - Promo+Sales |  | 3639986556
| W11 | RL Koos | Not Started Yet |  | 2023-03-18 |  |  | Team - Promo+Sales |  | 3639986617
| W12 | RL Koos | Not Started Yet |  | 2023-03-25 |  |  | Team - Promo+Sales |  | 3639986687
| W13 | RL Koos | Not Started Yet |  | 2023-03-31 |  |  | Team - Promo+Sales |  | 3639986773
Client Touches - See CRM |  | RL Koos | Not Started Yet | 2022-12-05 |  | 2023-01-03 | 2023-03-31 |  | 3639985308
| W1 | RL Koos | Not Started Yet |  | 2023-01-07 |  |  | PR Touch |  | 3639985851
| W2 | RL Koos | Not Started Yet |  | 2023-01-14 |  |  | PR Touch |  | 3639985892
| W3 | RL Koos | Not Started Yet |  | 2023-01-21 |  |  | PR Touch |  | 3639985991
| W4 | RL Koos | Not Started Yet |  | 2023-01-28 |  |  | PR Touch |  | 3639986075
| W5 | RL Koos | Not Started Yet |  | 2023-02-04 |  |  | PR Touch |  | 3639986162
| W6 | RL Koos | Not Started Yet |  | 2023-02-11 |  |  | PR Touch |  | 3639986241
| W7 | RL Koos | Not Started Yet |  | 2023-02-18 |  |  | PR Touch |  | 3639986322
| W8 | RL Koos | Not Started Yet |  | 2023-02-25 |  |  | PR Touch |  | 3639986404
| W9 | RL Koos | Not Started Yet |  | 2023-03-04 |  |  | PR Touch |  | 3639986493
| W10 | RL Koos | Not Started Yet |  | 2023-03-11 |  |  | PR Touch |  | 3639986609
| W11 | RL Koos | Not Started Yet |  | 2023-03-18 |  |  | PR Touch |  | 3639986679
| W12 | RL Koos | Not Started Yet |  | 2023-03-25 |  |  | PR Touch |  | 3639986748
| W13 | RL Koos | Not Started Yet |  | 2023-03-31 |  |  | PR Touch |  | 3639986808
Improve / Adapt |  | RL Koos | Not Started Yet |  |  | 2023-01-01 | 2023-03-31 |  | 3639985363
| Improvement Based on Results |  | Not Started Yet | [6 empty] | 3639985840
| Improvement Based on Results |  | Not Started Yet | [6 empty] | 3639985940
| Improvement Based on Results |  | Not Started Yet | [6 empty] | 3639986004
|  |  |  | 2022-12-05 to 2023-01-16 | 2023-01-15 to 2023-03-31 | 2023-01-01 | 2023-03-31
Referrals (fr Clients & Influencers)
Name | Subitems | Person | Status | Start Date | Due Date | Timeline - Start | Timeline - End | Summary Notes | Item ID (auto generated)
Plan & Prep (copy) |  | rkoos@peopleinsure.com | Working on it | 2022-12-05 |  | 2023-01-01 | 2023-01-15 |  | 3633528878
| Research | RL Koos | Not Started Yet |  |  |  |  | Team - Promo+Sales |  | 3633529365
| Map Campaign | RL Koos | Not Started Yet |  |  |  |  | Team - Promo+Sales |  | 3633528932
| Develop Content & Assets |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3633529139
| List - Reports fr AMS |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3633529250
| CRM Load Map & Content |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3633529179
| Setup KPI Measurement Tracking |  | Not Started Yet |  |  |  |  | Team - Promo+Sales | Track Results | 3633529339
| Train Staff |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3633529286
| Test & AB Test |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3633529216
SOP for Asking for Referrals |  | rkoos@peopleinsure.com | Working on it |  | 2022-12-31 | 2022-12-26 | 2022-12-28 | Prep ad hoc asks | 3615189399
| Determine Triggers |  | Not Started Yet | [6 empty] | 3615192830
| Write script |  | Not Started Yet | [6 empty] | 3615192073
| Practice & Role Play |  | Not Started Yet | [6 empty] | 3615192364
Develop Targeted Networking Campaign |  | rkoos@peopleinsure.com | Working on it |  | 2023-01-31 | 2023-01-01 | 2023-03-31 | Networking | 3615202236
| Identify Influencers |  | Not Started Yet |  | 2023-01-22 |  |  | Marketing Staff |  | 3615202291
| Research Influencers | RL Koos | Not Started Yet |  | 2023-01-22 |  |  | Marketing Staff |  | 3615202485
| Obtain Introductions | RL Koos | Not Started Yet |  | 2023-01-31 |  |  | PR Touch |  | 3615202362
| Nurture relationship | RL Koos | Not Started Yet |  |  |  |  | PR Touch |  | 3615202606
| Present offer | RL Koos | Not Started Yet |  | 2023-02-28 |  |  | PR Touch |  | 3615202640
Campaign Map - DRIP (copy) |  | rkoos@peopleinsure.com | Not Started Yet |  |  |  |  | Drip Campaign to Clients | 3633300167
| On Hold Message |  | Not Started Yet | [5 empty] | Continual | 3633421870
| LinkedIn & You Tube Video Post |  | Not Started Yet |  |  |  |  | Social Media/Online |  | 3633300221
| Email |  | Not Started Yet |  |  |  |  | CRM Email Automated |  | 3633300251
| Email |  | Not Started Yet |  |  |  |  | CRM Email Automated |  | 3633300272
| Email |  | Not Started Yet |  |  |  |  | CRM Email Automated |  | 3633300318
| Call |  | Not Started Yet |  |  |  |  | PR Touch | CRM Notifies PR #~ | 3633300335
| Client To Sold Onboarding Campaign |  | Not Started Yet |  |  |  |  | CSR | Call Result | 3633300367
| Client To Nurture Campaign |  | Not Started Yet |  |  |  |  | CRM Email Automated | Call Result | 3633300384
| SM Post 2 |  | Not Started Yet |  |  |  |  | Tech - SM Sched Post | Weekly | 3633300454
| SM Post 3 |  | Not Started Yet |  |  |  |  | Tech - SM Sched Post | Weekly | 3633300467
| SM Post 4 |  | Not Started Yet |  |  |  |  | Tech - SM Sched Post | Weekly | 3633300481
| SM Post 5 |  | Not Started Yet |  |  |  |  | Tech - SM Sched Post | Weekly | 3633300499
| SM Post 6 |  | Not Started Yet |  |  |  |  | Tech - SM Sched Post | Weekly | 3633300516
| SM Post 7 |  | Not Started Yet |  |  |  |  | Tech - SM Sched Post | Weekly | 3633300537
| SM Post 8 |  | Not Started Yet |  |  |  |  | Tech - SM Sched Post | Weekly | 3633300549
| SM Post 9 |  | Not Started Yet |  |  |  |  | Tech - SM Sched Post | Weekly | 3633300571
| SM Post 10 |  | Not Started Yet |  |  |  |  | Tech - SM Sched Post | Weekly | 3633300591
Launch (copy) | General launch, LinkedIn Posts, See CRM for tracking touches and sales KPIs, Beta Launch, Improvements | RL Koos, rkoos@peopleinsure.com | Not Started Yet | 2023-01-03 | 2023-03-31 | 2023-01-15 | 2023-04-12 |  | 3633566447
| Beta Launch |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3633566613
| Improvements |  | Not Started Yet |  |  |  |  | Team - Promo+Sales |  | 3633566662
| General launch | rkoos@peopleinsure.com | Not Started Yet |  | 2022-12-13 |  |  | Marketing Staff |  | 3633566526
| LinkedIn Posts | rkoos@peopleinsure.com | Not Started Yet |  |  |  |  | Tech - SM Sched Post |  | 3633566555
| See CRM for tracking touches and sales KPIs | RL Koos | Not Started Yet |  |  |  |  | CRM Entry | CRM docs touches not automated | 3633566583
Manage Campaign (copy) |  | rkoos@peopleinsure.com | Not Started Yet | [5 empty] | 3633540612
| Review CRM |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3633540655
| Test |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3633540669
| Resolve Issues |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3633540714
| Answer Questions |  | Not Started Yet |  |  |  |  | Team - Promo+Sales |  | 3633540738
| Improve |  | Not Started Yet |  |  |  |  | Team - Promo+Sales |  | 3633540688
KPI Review (copy) |  | RL Koos | Not Started Yet | 2022-12-05 |  |  |  |  | 3633572953
| W1 | RL Koos | Not Started Yet |  | 2023-01-07 |  |  | Team - Promo+Sales |  | 3633573109
| W2 | RL Koos | Not Started Yet |  | 2023-01-14 |  |  | Team - Promo+Sales |  | 3633573214
| W3 | RL Koos | Not Started Yet |  | 2023-01-21 |  |  | Team - Promo+Sales |  | 3633573293
| W4 | RL Koos | Not Started Yet |  | 2023-01-28 |  |  | Team - Promo+Sales |  | 3633573386
| W5 | RL Koos | Not Started Yet |  | 2023-02-04 |  |  | Team - Promo+Sales |  | 3633573452
| W6 | RL Koos | Not Started Yet |  | 2023-02-11 |  |  | Team - Promo+Sales |  | 3633573517
| W7 | RL Koos | Not Started Yet |  | 2023-02-18 |  |  | Team - Promo+Sales |  | 3633573586
| W8 | RL Koos | Not Started Yet |  | 2023-02-25 |  |  | Team - Promo+Sales |  | 3633573658
| W9 | RL Koos | Not Started Yet |  | 2023-03-04 |  |  | Team - Promo+Sales |  | 3633573724
| W10 | RL Koos | Not Started Yet |  | 2023-03-11 |  |  | Team - Promo+Sales |  | 3633573787
| W11 | RL Koos | Not Started Yet |  | 2023-03-18 |  |  | Team - Promo+Sales |  | 3633573868
| W12 | RL Koos | Not Started Yet |  | 2023-03-25 |  |  | Team - Promo+Sales |  | 3633573958
| W13 | RL Koos | Not Started Yet |  | 2023-03-31 |  |  | Team - Promo+Sales |  | 3633574058
Client Touches - See CRM (copy) |  | RL Koos | Not Started Yet | 2022-12-05 |  | 2023-01-03 | 2023-03-31 |  | 3633590324
| W1 | RL Koos | Not Started Yet |  | 2023-01-07 |  |  | PR Touch |  | 3633590493
| W2 | RL Koos | Not Started Yet |  | 2023-01-14 |  |  | PR Touch |  | 3633590565
| W3 | RL Koos | Not Started Yet |  | 2023-01-21 |  |  | PR Touch |  | 3633590619
| W4 | RL Koos | Not Started Yet |  | 2023-01-28 |  |  | PR Touch |  | 3633590662
| W5 | RL Koos | Not Started Yet |  | 2023-02-04 |  |  | PR Touch |  | 3633590716
| W6 | RL Koos | Not Started Yet |  | 2023-02-11 |  |  | PR Touch |  | 3633590776
| W7 | RL Koos | Not Started Yet |  | 2023-02-18 |  |  | PR Touch |  | 3633590815
| W8 | RL Koos | Not Started Yet |  | 2023-02-25 |  |  | PR Touch |  | 3633590868
| W9 | RL Koos | Not Started Yet |  | 2023-03-04 |  |  | PR Touch |  | 3633590924
| W10 | RL Koos | Not Started Yet |  | 2023-03-11 |  |  | PR Touch |  | 3633590980
| W11 | RL Koos | Not Started Yet |  | 2023-03-18 |  |  | PR Touch |  | 3633591024
| W12 | RL Koos | Not Started Yet |  | 2023-03-25 |  |  | PR Touch |  | 3633591075
| W13 | RL Koos | Not Started Yet |  | 2023-03-31 |  |  | PR Touch |  | 3633591122
Improve / Adapt (copy) |  | RL Koos | Not Started Yet | [5 empty] | 3633596383
| Improvement Based on Results |  | Not Started Yet | [6 empty] | 3633596418
| Improvement Based on Results |  | Not Started Yet | [6 empty] | 3633596433
| Improvement Based on Results |  | Not Started Yet | [6 empty] | 3633596449
|  |  |  | 2022-12-05 to 2023-01-03 | 2022-12-31 to 2023-03-31 | 2022-12-26 | 2023-04-12
NBS - Niche Market 60%
Name | Subitems | Person | Status | Start Date | Due Date | Timeline - Start | Timeline - End | Summary Notes | Item ID (auto generated)
Research |  | rkoos@peopleinsure.com | Working on it |  | 2023-01-31 | 2023-01-01 | 2023-01-15 |  | 3615199412
| Research Industry | RL Koos, rkoos@peopleinsure.com | Getting It Done |  | 2023-01-08 |  |  | Team - Promo+Sales | RLK & LMM research | 3615200785
| Competitive Analysis | rkoos@peopleinsure.com | Not Started Yet |  | 2023-01-08 |  |  |  |  | 3615200420
| Develop Persona(s) |  | Not Started Yet |  | 2023-01-08 |  |  |  |  | 3615199603
| Develop Solution - Policies + |  | Not Started Yet |  | 2023-01-08 |  |  |  |  | 3615199653
| Develop Campaign Strategy |  | Not Started Yet |  | 2023-01-15 |  |  |  |  | 3648265789
| ID Messaging concepts |  | Not Started Yet |  | 2023-01-15 |  |  |  |  | 3615199701
| ID Topics for Speaking/Content |  | Not Started Yet |  | 2023-01-15 |  |  |  |  | 3615200157
| ID Influencers |  | Not Started Yet | [6 empty] | 3648305604
| ID Industry Ad Options |  | Not Started Yet |  | 2023-01-15 |  |  |  |  | 3615199539
| ID Speaking Opportunities |  | Not Started Yet |  | 2023-01-15 |  |  |  |  | 3615199793
| ID Where you will find personas |  | Not Started Yet |  | 2023-01-15 |  |  |  |  | 3615203207
| ID Tech tools |  | Not Started Yet |  | 2023-01-15 |  |  |  |  | 3615861447
| Get Feedback |  | Not Started Yet |  | 2023-01-31 |  |  |  |  | 3615861497
Plan & Prep |  | rkoos@peopleinsure.com | Completed | 2022-12-05 |  | 2023-01-15 | 2023-01-31 |  | 3633529413
| Gather Resources | RL Koos | Not Started Yet |  |  |  |  | Team - Promo+Sales |  | 3633529562
| Map Lead Campaign | RL Koos | Not Started Yet |  |  |  |  | Team - Promo+Sales |  | 3633529438
| Develop Content & Assets |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3633529473
| Lists - Buy, Partner or Develop |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3633529516
| CRM Load Map & Content |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3633529488
| Setup KPI Measurement Tracking |  | Not Started Yet |  |  |  |  | Team - Promo+Sales | Track Results | 3633529550
| Train Staff |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3633529531
| Alpha Test |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3633529502
| Get first speaking engagement |  | Not Started Yet |  | 2023-01-31 |  |  |  |  | 3615199876
Networking |  | rkoos@peopleinsure.com | Working on it |  |  | 2023-02-01 | 2023-02-15 |  | 3633666537
| ID Influencers |  | Not Started Yet |  | 2023-01-22 |  |  | Team - Promo+Sales |  | 3633666612
| ID HV Leads for Networking |  | Not Started Yet | [6 empty] | 3648319268
| Research Individuals |  | Not Started Yet |  | 2023-01-22 |  |  | Team - Promo+Sales |  | 3633666667
| Map HVL Campaign |  | Not Started Yet | [6 empty] | 3648307698
| Map Influencer Campaign |  | Not Started Yet | [6 empty] | 3648306544
| Obtain Introductions |  | Not Started Yet |  | 2023-01-31 |  |  | PR Touch |  | 3633666644
| Nurture relationship |  | Not Started Yet |  |  |  |  | PR Touch |  | 3633666699
| Obtain Appointment(s) |  | Not Started Yet | [6 empty] | 3648323785
| Present offer |  | Not Started Yet |  | 2023-02-28 |  |  | PR Touch |  | 3633666722
Campaign Map |  | rkoos@peopleinsure.com | Not Started Yet |  |  |  |  | Campaign to Attract Qualified Leads | 3633627868
| LinkedIn & You Tube Video Post |  | Not Started Yet |  |  |  |  | Social Media/Online |  | 3633627960
| Lead Magnet |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3633706157
| Ad 1 - Industry Mag |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3633717466
| Ad 2 - LinkedIn |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3633740181
| Ad 3 - YouTube |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3633745495
| Speak 1 |  | Not Started Yet |  |  |  |  | PR Touch |  | 3633722874
| Speak 2 |  | Not Started Yet |  |  |  |  | PR Touch |  | 3633733269
| Speak 3 |  | Not Started Yet |  |  |  |  | PR Touch |  | 3633749610
| SM Post 2 |  | Not Started Yet |  |  |  |  | Tech - SM Sched Post | Weekly | 3633628941
| SM Post 3 |  | Not Started Yet |  |  |  |  | Tech - SM Sched Post | Weekly | 3633630777
| SM Post 4 |  | Not Started Yet |  |  |  |  | Tech - SM Sched Post | Weekly | 3633630895
| SM Post 5 |  | Not Started Yet |  |  |  |  | Tech - SM Sched Post | Weekly | 3633631089
| SM Post 6 |  | Not Started Yet |  |  |  |  | Tech - SM Sched Post | Weekly | 3633631181
| SM Post 7 |  | Not Started Yet |  |  |  |  | Tech - SM Sched Post | Weekly | 3633631278
| SM Post 8 |  | Not Started Yet |  |  |  |  | Tech - SM Sched Post | Weekly | 3633631393
| SM Post 9 |  | Not Started Yet |  |  |  |  | Tech - SM Sched Post | Weekly | 3633631470
| SM Post 10 |  | Not Started Yet |  |  |  |  | Tech - SM Sched Post | Weekly | 3633631575
| Subscribe |  | Not Started Yet | [6 empty] | 3633707771
| Email |  | Not Started Yet |  |  |  |  | CRM Email Automated |  | 3633628013
| Email |  | Not Started Yet |  |  |  |  | CRM Email Automated |  | 3633628053
| Email |  | Not Started Yet |  |  |  |  | CRM Email Automated |  | 3633628230
| Call |  | Not Started Yet |  |  |  |  | PR Touch | CRM Notifies PR #~ | 3633628339
| Lead to Appointment Campaign |  | Not Started Yet |  |  |  |  | CSR | Call Result | 3633628687
| Lead To Nurture Campaign |  | Not Started Yet |  |  |  |  | CRM Email Automated | Call Result | 3633628821
Launch |  | RL Koos, rkoos@peopleinsure.com | Not Started Yet | 2023-01-03 | 2023-03-31 | 2023-02-01 | 2023-02-15 |  | 3633565836
| Beta Launch |  | Not Started Yet |  |  | 2023-02-01 | 2023-02-15 | Marketing Staff |  | 3633565965
| Improvements |  | Not Started Yet |  |  | 2023-02-16 | 2023-02-28 | Team - Promo+Sales |  | 3633565980
| General launch | rkoos@peopleinsure.com | Not Started Yet |  | 2022-12-13 | 2023-03-01 | 2023-03-31 | Marketing Staff |  | 3633565892
| LinkedIn Posts | rkoos@peopleinsure.com | Not Started Yet |  |  |  |  | Tech - SM Sched Post |  | 3633565915
| See CRM for tracking touches and sales KPIs | RL Koos | Not Started Yet |  |  |  |  | CRM Entry | CRM docs touches not automated | 3633565938
Manage Campaign |  | rkoos@peopleinsure.com | Not Started Yet |  |  | 2023-03-01 | 2023-03-31 |  | 3633541176
| Review CRM |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3633541205
| Test |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3633541223
| Resolve Issues |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3633541251
| Answer Questions |  | Not Started Yet |  |  |  |  | Team - Promo+Sales |  | 3633541263
| Improve |  | Not Started Yet |  |  |  |  | Team - Promo+Sales |  | 3633541236
KPI Review |  | RL Koos | Not Started Yet | 2022-12-05 |  |  |  |  | 3633572300
| W1 | RL Koos | Not Started Yet |  | 2023-01-07 |  |  | Team - Promo+Sales |  | 3633572436
| W2 | RL Koos | Not Started Yet |  | 2023-01-14 |  |  | Team - Promo+Sales |  | 3633572490
| W3 | RL Koos | Not Started Yet |  | 2023-01-21 |  |  | Team - Promo+Sales |  | 3633572752
| W4 | RL Koos | Not Started Yet |  | 2023-01-28 |  |  | Team - Promo+Sales |  | 3633572795
| W5 | RL Koos | Not Started Yet |  | 2023-02-04 |  |  | Team - Promo+Sales |  | 3633572847
| W6 | RL Koos | Not Started Yet |  | 2023-02-11 |  |  | Team - Promo+Sales |  | 3633572918
| W7 | RL Koos | Not Started Yet |  | 2023-02-18 |  |  | Team - Promo+Sales |  | 3633572969
| W8 | RL Koos | Not Started Yet |  | 2023-02-25 |  |  | Team - Promo+Sales |  | 3633573093
| W9 | RL Koos | Not Started Yet |  | 2023-03-04 |  |  | Team - Promo+Sales |  | 3633573141
| W10 | RL Koos | Not Started Yet |  | 2023-03-11 |  |  | Team - Promo+Sales |  | 3633573200
| W11 | RL Koos | Not Started Yet |  | 2023-03-18 |  |  | Team - Promo+Sales |  | 3633573251
| W12 | RL Koos | Not Started Yet |  | 2023-03-25 |  |  | Team - Promo+Sales |  | 3633573295
| W13 | RL Koos | Not Started Yet |  | 2023-03-31 |  |  | Team - Promo+Sales |  | 3633573351
Client Touches - See CRM |  | RL Koos | Not Started Yet | 2022-12-05 |  | 2023-01-03 | 2023-03-31 |  | 3633591502
| W1 | RL Koos | Not Started Yet |  | 2023-01-07 |  |  | PR Touch |  | 3633591690
| W2 | RL Koos | Not Started Yet |  | 2023-01-14 |  |  | PR Touch |  | 3633591787
| W3 | RL Koos | Not Started Yet |  | 2023-01-21 |  |  | PR Touch |  | 3633591911
| W4 | RL Koos | Not Started Yet |  | 2023-01-28 |  |  | PR Touch |  | 3633591998
| W5 | RL Koos | Not Started Yet |  | 2023-02-04 |  |  | PR Touch |  | 3633592100
| W6 | RL Koos | Not Started Yet |  | 2023-02-11 |  |  | PR Touch |  | 3633592197
| W7 | RL Koos | Not Started Yet |  | 2023-02-18 |  |  | PR Touch |  | 3633592306
| W8 | RL Koos | Not Started Yet |  | 2023-02-25 |  |  | PR Touch |  | 3633592447
| W9 | RL Koos | Not Started Yet |  | 2023-03-04 |  |  | PR Touch |  | 3633592548
| W10 | RL Koos | Not Started Yet |  | 2023-03-11 |  |  | PR Touch |  | 3633592627
| W11 | RL Koos | Not Started Yet |  | 2023-03-18 |  |  | PR Touch |  | 3633592703
| W12 | RL Koos | Not Started Yet |  | 2023-03-25 |  |  | PR Touch |  | 3633592772
| W13 | RL Koos | Not Started Yet |  | 2023-03-31 |  |  | PR Touch |  | 3633592852
Improve / Adapt |  | RL Koos | Not Started Yet | [5 empty] | 3633595966
| Improvement Based on Results |  | Not Started Yet | [6 empty] | 3633596019
| Improvement Based on Results |  | Not Started Yet | [6 empty] | 3633596036
| Improvement Based on Results |  | Not Started Yet | [6 empty] | 3633596052
|  |  |  | 2022-12-05 to 2023-01-03 | 2023-01-31 to 2023-03-31 | 2023-01-01 | 2023-03-31
NBS - General Lines 40%
Plan & Prep |  | rkoos@peopleinsure.com | Not Started Yet | 2022-12-05 |  | 2023-01-01 | 2023-01-15 |  | 3633529741
| Research | RL Koos | Not Started Yet |  |  |  |  | Team - Promo+Sales |  | 3633530801
| Map Campaign | RL Koos | Not Started Yet |  |  |  |  | Team - Promo+Sales |  | 3633529798
| Develop Content & Assets |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3633530562
| List - Reports fr AMS |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3633530741
| CRM Load Map & Content |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3633530691
| Setup KPI Measurement Tracking |  | Not Started Yet |  |  |  |  | Team - Promo+Sales | Track Results | 3633530786
| Train Staff |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3633530765
| Test & AB Test |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3633530711
R&D Marketing |  | rkoos@peopleinsure.com | Not Started Yet |  | 2023-01-31 | 2023-01-01 | 2023-01-31 |  | 3615203848
| Develop persona |  | Not Started Yet |  | 2023-01-12 |  |  |  |  | 3615203860
| ID where persona is |  | Not Started Yet |  | 2023-01-22 |  |  |  |  | 3615203858
| Develop solution |  | Not Started Yet |  | 2023-01-15 |  |  |  |  | 3615203862
| Develop messaging |  | Not Started Yet |  | 2023-01-19 |  |  |  |  | 3615203864
| Develop Online Campaign |  | Not Started Yet | [6 empty] | 3615203875
| Develop assets |  | Not Started Yet |  | 2023-01-26 |  |  |  |  | 3615203859
| Train staff |  | Not Started Yet |  | 2023-01-22 |  |  |  |  | 3615203865
| ID 5 topics for videos |  | Not Started Yet |  | 2023-01-22 |  |  |  |  | 3615203869
| Produce 5 Videos |  | Not Started Yet |  | 2023-01-31 |  |  |  |  | 3615203871
Networking |  | rkoos@peopleinsure.com | Not Started Yet |  |  | 2023-01-01 | 2023-03-31 |  | 3615203846
| Identify Influencers |  | Not Started Yet |  | 2023-01-22 |  |  | Team - Promo+Sales |  | 3615203850
| Research Influencers |  | Not Started Yet |  | 2023-01-22 |  |  | Team - Promo+Sales |  | 3615203853
| Obtain Introductions |  | Not Started Yet |  | 2023-01-31 |  |  | PR Touch |  | 3615203851
| Nurture relationship |  | Not Started Yet |  |  |  |  | PR Touch |  | 3615203854
| Present offer |  | Not Started Yet |  | 2023-02-28 |  |  | PR Touch |  | 3615203855
Campaign Map |  | rkoos@peopleinsure.com | Not Started Yet |  |  |  |  | Campaign to Attract Qualified Leads | 3633757789
| LinkedIn & You Tube Video Post |  | Not Started Yet |  |  |  |  | Social Media/Online |  | 3633757853
| Lead Magnet |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3633758262
| Ad 1 - Newspaper |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3633758303
| Ad 2 - LinkedIn |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3633757874
| Ad 3 - Google Local |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3633757895
| Speak 1 |  | Not Started Yet |  |  |  |  | PR Touch |  | 3633758322
| Speak 2 |  | Not Started Yet |  |  |  |  | PR Touch |  | 3633757851
| Speak 3 |  | Not Started Yet |  |  |  |  | PR Touch |  | 3633757915
| SM Post 2 |  | Not Started Yet |  |  |  |  | Tech - SM Sched Post | Weekly | 3633758032
| SM Post 3 |  | Not Started Yet |  |  |  |  | Tech - SM Sched Post | Weekly | 3633758054
| SM Post 4 |  | Not Started Yet |  |  |  |  | Tech - SM Sched Post | Weekly | 3633758085
| SM Post 5 |  | Not Started Yet |  |  |  |  | Tech - SM Sched Post | Weekly | 3633758117
| SM Post 6 |  | Not Started Yet |  |  |  |  | Tech - SM Sched Post | Weekly | 3633758149
| SM Post 7 |  | Not Started Yet |  |  |  |  | Tech - SM Sched Post | Weekly | 3633758171
| SM Post 8 |  | Not Started Yet |  |  |  |  | Tech - SM Sched Post | Weekly | 3633758199
| SM Post 9 |  | Not Started Yet |  |  |  |  | Tech - SM Sched Post | Weekly | 3633758219
| SM Post 10 |  | Not Started Yet |  |  |  |  | Tech - SM Sched Post | Weekly | 3633758239
| Subscribe |  | Not Started Yet | [6 empty] | 3633758281
| Email |  | Not Started Yet |  |  |  |  | CRM Email Automated |  | 3633757877
| Email |  | Not Started Yet |  |  |  |  | CRM Email Automated |  | 3633757907
| Email |  | Not Started Yet |  |  |  |  | CRM Email Automated |  | 3633757925
| Call |  | Not Started Yet |  |  |  |  | PR Touch | CRM Notifies PR #~ | 3633757962
| Lead to Appointment Campaign |  | Not Started Yet |  |  |  |  | CSR | Call Result | 3633757988
| Lead To Nurture Campaign |  | Not Started Yet |  |  |  |  | CRM Email Automated | Call Result | 3633758011
Launch |  | RL Koos, rkoos@peopleinsure.com | Not Started Yet | 2023-01-03 | 2023-03-31 | 2023-01-15 | 2023-04-12 |  | 3633567015
| Beta Launch |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3633567133
| Improvements |  | Not Started Yet |  |  |  |  | Team - Promo+Sales |  | 3633567153
| General launch | rkoos@peopleinsure.com | Not Started Yet |  | 2022-12-13 |  |  | Marketing Staff |  | 3633567054
| LinkedIn Posts | rkoos@peopleinsure.com | Not Started Yet |  |  |  |  | Tech - SM Sched Post |  | 3633567075
| See CRM for tracking touches and sales KPIs | RL Koos | Not Started Yet |  |  |  |  | CRM Entry | CRM docs touches not automated | 3633567102
Manage Campaign |  | rkoos@peopleinsure.com | Not Started Yet | [5 empty] | 3633541524
| Review CRM |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3633541563
| Test |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3633541600
| Resolve Issues |  | Not Started Yet |  |  |  |  | Marketing Staff |  | 3633541643
| Answer Questions |  | Not Started Yet |  |  |  |  | Team - Promo+Sales |  | 3633541675
| Improve |  | Not Started Yet |  |  |  |  | Team - Promo+Sales |  | 3633541616
KPI Review |  | RL Koos | Not Started Yet | 2022-12-05 |  |  |  |  | 3633573770
Client Touches - See CRM (copy) | W1, W2, W3, W4, W5, W6, W7, W8, W9, W10, W11, W12, W13 | RL Koos | Not Started Yet | 2022-12-05 |  | 2023-01-03 | 2023-03-31 |  | 3633589387
| W1 | RL Koos | Not Started Yet |  | 2023-01-07 |  |  | PR Touch |  | 3633589937
| W2 | RL Koos | Not Started Yet |  | 2023-01-14 |  |  | PR Touch |  | 3633590035
| W3 | RL Koos | Not Started Yet |  | 2023-01-21 |  |  | PR Touch |  | 3633590110
| W4 | RL Koos | Not Started Yet |  | 2023-01-28 |  |  | PR Touch |  | 3633590220
| W5 | RL Koos | Not Started Yet |  | 2023-02-04 |  |  | PR Touch |  | 3633590275
| W6 | RL Koos | Not Started Yet |  | 2023-02-11 |  |  | PR Touch |  | 3633590344
| W7 | RL Koos | Not Started Yet |  | 2023-02-18 |  |  | PR Touch |  | 3633590426
| W8 | RL Koos | Not Started Yet |  | 2023-02-25 |  |  | PR Touch |  | 3633590509
| W9 | RL Koos | Not Started Yet |  | 2023-03-04 |  |  | PR Touch |  | 3633590594
| W10 | RL Koos | Not Started Yet |  | 2023-03-11 |  |  | PR Touch |  | 3633590665
| W11 | RL Koos | Not Started Yet |  | 2023-03-18 |  |  | PR Touch |  | 3633590737
| W12 | RL Koos | Not Started Yet |  | 2023-03-25 |  |  | PR Touch |  | 3633590788
| W13 | RL Koos | Not Started Yet |  | 2023-03-31 |  |  | PR Touch |  | 3633590845
Improve / Adapt (copy) |  | RL Koos | Not Started Yet | [5 empty] | 3633595610
| Improvement Based on Results |  | Not Started Yet | [6 empty] | 3633595657
| Improvement Based on Results |  | Not Started Yet | [6 empty] | 3633595687
| Improvement Based on Results |  | Not Started Yet | [6 empty] | 3633595711

## q1-action-plan-updates
Q1 Action Plan | Updates
Item ID | Item Name | Content Type | Content Type | User | Created At | Update Content | Likes Count | Asset IDs | Post ID | Parent Post ID
3615071871 | Strategy | Update |  | RL Koos | 03/December/2022 06:32:36 PM | Strategy / Approach Attract high quality leads, convert them to raving fan clients with high LCV (Retension + RPC) who refer others using omni-channel, integrated marketing and sales campaigns. 93.3% Existing clients / 6.4% New clients. NBS: 60% Special Mkt Segment, 40% General Lines ﻿ Core Principles Work as Trusted Advisor with integrity. Add value for all stakeholders. | 0 |  | 1847932701
3615071872 | Goal | Update |  | RL Koos | 03/December/2022 06:22:53 PM | What I’m Accomplishing Grow Commission Revenue organically by 20% by 12/31/23 ﻿ Why It’s Important >* Take good care of my family * Pride, Duty, Accomplishment * Sets me up to buy my own agency How it Looks, Feels, … I feel like a hero spouse, parent and producer. I can do anything. I feel proud. I'm having fun. My dream is so close I can almost touch it. ﻿ What’s at stake if I miss If I missed my goals I'd let down my family and boss who believed/trusted in me. I would have financial struggles and not enjoy my work as much. | 0 |  | 1847931612
3615071873 | High Level Plan | Update |  | RL Koos | 03/December/2022 06:41:01 PM | Existing Client Campaign: Q1) Missing Major Lines Q2) EPLI Q3) Cyber Q4) Cross-sell employees ﻿ ﻿New Business ﻿Referrals Q1) Create Standard Op Procedure to ask for referral every time someone thanks us or says something nice Q2) Referral campaign 1 Q3) Referral campaign 2 Q4) Referral campaign 3 ﻿ ﻿﻿New business Q1) Campaign to raise awareness/trust and build small business list using LinkedIn, SEO and online ads to drive to videos, lead magnet, etc.; Network to target specific high value prospects/gatekeepers Q2) Add campaign with targeted ads online & industry periodicals; continue to build list & specifically target/nurture high value prospects/gatekeepers Q3) Campaign to segment & qualify list, nurture those not ready to quote yet, fill pipeline with those ready to quote Q4) Campaigns expanded to include Ads. | 0 |  | 1847933596
3615071874 | KPI Review | Update |  | RL Koos | 03/December/2022 08:49:33 PM | ﻿KPIs are tracked in CRM. Run reports and review KPIs | 0 |  | 1847971790
3615100172 | KPIs | Update |  | RL Koos | 03/December/2022 06:52:42 PM | KPIs with Timeframes Total Commission Income >* Current Earnings: $100,000 commission income. * Goal: Increase by 20% * 100,000 ﻿+20,000 = 120,000/year total commission income * 10,000/month * 2,500/week ﻿Retention >* Current 90% = $90,000 New Business>* 120,000 – 90,000 = $30,000/year New Business Required >* $7500 / Qtr * $2500/mo * $600/week (50wk) Ave Commission/Sale: >* Current $500 * Increase to $600 Actions >* 1 new client / week @ $600 * 5 appointments * 2 proposals * 100 cold leads (Calls, add to list, etc) Nurture 1 value add touch per week | 0 |  | 1847934664
3615100411 | Performance Level | Update |  | RL Koos | 03/December/2022 06:53:55 PM | Performance Level Level up my performance from 5 to 6 to 7 Become a top 25% performer Improve Sales skills for high-impact presentations, overcoming objections, etc. Implement a new sales process to help myself and other producers sell more ﻿Read 1 book a month on improving my sales & presentation skills. Take a sales class. Get a performance coach to help me improve my skills & performance; provide strategy, feedback and accountability to speed up my success | 0 |  | 1847934799
3615199412 | Research | Update |  | RL Koos | 04/December/2022 08:00:41 AM | Complete the research into the industry/niche market to be able to develop a high-impact an omni-channel sales and marketing plan to build my reputation as a Trusted Advisor that adds great value in the __ industry. Initial focus on LinkedIn, industry periodicals and podcast ads, speaking at industry meetings and networking to attract leads in the industry. ﻿﻿If you need more help on with developing high-impact sales and marketing campaigns, contact PeopleInsure at (877)772-4677 or ask@peopleinsure.com. | 0 |  | 1848184628
3615202236 | Develop Targeted Networking Campaign | Update |  | RL Koos | 04/December/2022 08:02:14 AM | ﻿Develop a networking campaign to identify and enroll industry influencers as raving fans who refer us to others. Possibly find a partnership opportunity with industry leader(s). | 0 |  | 1848185587
3633591502 | Client Touches - See CRM | Update |  | RL Koos | 10/December/2022 09:32:54 AM | Where to track? Each agency uses different tools. Typically: ﻿Pre-Sale CRM Typically, ﻿automated client touches (ex: emails) are tracked in your CRM. Analytics on the metrics for these are CRM reports. Sales Enablement: Individual, non-automated ﻿Client touches are typically tracked in your sales enablement software, such as SalesForce, your pipeline manager, your CRM, etc.. These are individual pre-sale touches from the Producer or staff, such as phone calls, individually sent emails, appointments, presentations, etc. ﻿Post Sale ﻿Agency Management System (AMS): Typically, once the client is bound, all touches are tracked in the agency's agency management software. Often a summary report is printed from the sales enablement software and attached as in the AMS document management function.﻿﻿ ﻿﻿If you need more help on with CRMs, sales enablement tech or your AMS, contact PeopleInsure at (877)772-4677 or ask@peopleinsure.com. | 0 |  | 1860424517
3639985201 | KPI Review | Update |  | RL Koos | 03/December/2022 08:49:33 PM | ﻿KPIs are tracked in CRM. Run reports and review KPIs | 0 |  | 1857312794